Nexus Between Monitoring and Evaluation Practices and Performance of Competency-Based Curriculum Infrastructure Projects in Nairobi City County, Kenya

.

ABSTRACT

This study investigated the impact of Monitoring and Evaluation (M&E) practices on the performance of CBC infrastructure projects in Nairobi City County, Kenya. It specifically focused on M&E planning, baseline studies, stakeholder engagement, and performance reviews. Grounded in Stakeholder Theory, Performance Theory, and Results-Based Management Theory, the research employed a descriptive design targeting 101 CBC classroom projects executed between 2022 and 2023. Data were gathered from school principals and Sub-County Education Directors through semi-structured questionnaires and interview schedules, with a pilot study conducted in Kiambu County to validate the research instruments. Quantitative data were analyzed using descriptive statistics, Pearson correlation, and multiple regression analysis, while qualitative data were examined thematically. The findings indicated that M&E practices have a significant impact on project performance, collectively accounting for 78.8% of the variation in outcomes. In particular, M&E planning (β1 = 0.345, p = 0.00), baseline studies (β2 = 0.226, p = 0.01), and stakeholder engagement (β3 = 0.361, p = 0.00) emerged as statistically significant predictors of enhanced cost efficiency, timeliness, and quality. Conversely, M&E performance reviews (β4 = 0.059, p = 0.57) were not statistically significant, suggesting a limited use of feedback in decision-making processes. The study concludes that effective M&E planning, evidence-based baseline assessments, and inclusive stakeholder participation are critical determinants of successful CBC infrastructure delivery, while inadequate integration of performance review findings constrains adaptive management. It is recommended that education authorities strengthen institutional M&E frameworks, standardise planning tools, enhance capacity building, institutionalise regular baseline assessments, and improve feedback utilization systems to promote accountability, efficiency, and sustainability in public school infrastructure projects.

Keywords: Monitoring and Evaluation, CBC infrastructure, project performance, baseline studies, stakeholder engagement, performance reviews.

1. INTRODUCTION

Globally, the effectiveness of public infrastructure projects remains a significant issue, as numerous initiatives continue to face cost overruns, delays, and quality shortcomings despite considerable financial investments. These inefficiencies hinder the attainment of development goals and restrict the realization of socio-economic advantages linked to infrastructure development (Pereira et al., 2022). Evidence from both advanced and emerging economies shows that inadequate project oversight, poor coordination, and insufficient performance tracking systems play a crucial role in these outcomes. Specifically, shortcomings in Monitoring and Evaluation (M&E) systems restrict project managers' capacity to identify deviations early, enforce accountability, and ensure that projects are completed within the defined scope, timeline, and budget (Aloyce et al., 2024). In Africa, the situation is even more severe, with over 50% of public infrastructure projects historically failing to meet their intended goals due to inadequate planning, limited stakeholder engagement, and weak institutional frameworks (Elle, 2022). In Kenya, despite an increase in public spending on infrastructure particularly in the education sector projects continue to encounter ongoing issues such as delays, cost overruns, and quality problems. The Competency-Based Curriculum (CBC) infrastructure initiative, which aimed to build classrooms to facilitate the transition to junior secondary education, has been criticized for poor construction quality, lack of cost standardization, and implementation inefficiencies as noted in audit reports (OAG, 2024). These challenges highlight systemic weaknesses in project management, especially regarding the effective application of M&E practices.

While the existing literature acknowledges monitoring and evaluation (M&E) as a vital factor influencing project performance, several deficiencies persist. Firstly, previous research has largely focused on individual aspects of M&E practices such as stakeholder engagement, baseline assessments, or performance evaluations without synthesizing these components into a unified analytical framework. Secondly, numerous empirical investigations have concentrated on sectors like transport and energy infrastructure, with scant attention paid to education infrastructure projects, especially those related to the CBC in Kenya. Moreover, although audit reports and sectoral evaluations have pointed out shortcomings in the performance of CBC infrastructure projects particularly regarding timeliness, cost efficiency, and quality there is a lack of empirical evidence connecting these performance results to specific M&E practices within Nairobi City County. This results in both a contextual and empirical void in comprehending how integrated M&E practices affect the performance of education infrastructure projects.

In order to address these deficiencies, this research investigates the relationship between monitoring and evaluation practices and the performance of community-based construction (CBC) infrastructure projects in Nairobi City County, Kenya. The study specifically concentrates on essential M&E elements: planning, baseline studies, stakeholder engagement, and performance reviews, and evaluates their impact on project performance, which is measured in terms of timeliness, cost efficiency, and beneficiary satisfaction. By implementing a more holistic and integrated approach to M&E practices, and employing methodological triangulation, this research aims to produce strong empirical evidence that can guide policy decisions, enhance project management practices, and improve the effectiveness of future infrastructure initiatives within the education sector. Ultimately, this study contributes to the enhancement of accountability, efficiency, and sustainable results in the development of public infrastructure.

1.1 Research Objectives

- To analyse how M&E planning influences the performance of CBC infrastructure projects in Nairobi City County, Kenya.

- To evaluate the impact of M&E baseline assessments on the performance of CBC infrastructure projects in Nairobi City County, Kenya.

- To examine the role of stakeholder participation in M&E in shaping the performance of CBC infrastructure projects in Nairobi City County, Kenya.

- To investigate the effect of M&E performance review processes on the performance of CBC infrastructure projects in Nairobi City County, Kenya.

2. LITERATURE REVIEW

2.1 Theoretical Foundation

The connection between Monitoring and Evaluation (M&E) practices and project performance is based on three interrelated theoretical frameworks: the Theory of Performance, Stakeholder Theory, and Results-Based Management (RBM) Theory. The Theory of Performance, proposed by Elger (2007), defines performance as the achievement of valued outcomes that arise from intentional actions. This theory asserts that performance develops incrementally and is shaped by various factors, including knowledge, skills, context, and individual characteristics. It also indicates that performance can be assessed through indicators such as quality, efficiency, and the accomplishment of goals. In the context of projects, this viewpoint highlights that the effective use of resources including M&E systems improves outcomes like timeliness, cost-effectiveness, and quality. Therefore, this theory lays the groundwork for understanding project performance as a multifaceted concept. Stakeholder Theory, introduced by Freeman (1984), stresses that organizations must consider the interests of a wide range of stakeholders beyond just shareholders. It contends that stakeholders including beneficiaries, government bodies, financiers, and communities are crucial in shaping project outcomes. Engaging stakeholders effectively through participatory M&E fosters accountability, legitimacy, and sustainability. Nonetheless, the theory also recognizes the practical difficulties in reconciling conflicting stakeholder interests and implementing stakeholder priorities, as noted by Jensen in 2002. In this research, the theory guides the understanding of how stakeholder participation in M&E processes influences project performance. The Results-Based Management (RBM) Theory, linked to scholars like Mayne (2007), focuses on achieving quantifiable outcomes through organized planning, monitoring, and evaluation. RBM shifts the emphasis from inputs and activities to outputs and outcomes, thereby encouraging accountability and decision-making based on evidence, as highlighted by UNDP (2011). Key principles include goal setting, performance measurement, continuous monitoring, and adaptive learning. Despite its strengths, RBM faces challenges such as over-reliance on quantifiable indicators and the need for robust data systems. In this study, RBM underpins M&E planning, baseline studies, and performance reviews as mechanisms for enhancing project outcomes.

2.2 Empirical Review

Empirical evidence consistently shows that M&E planning has a significant impact on project performance. Research conducted in Kenya indicates that well-structured planning processes such as the definition of indicators, resource allocation, and activity scheduling positively influence project outcomes (Kamau & Muchelule, 2024). Comparable results have been observed in Uganda and Namibia, where M&E planning was found to improve efficiency, timeliness, and cost management (Ayebare, 2019; Tarindwa, 2019). In Rwanda, Muhayimana and Kamuhanda (2020) demonstrated that planning, when paired with participatory methods and the dissemination of M&E findings, enhances project timeliness and cost-effectiveness. Similarly, Olaremi et al. (2024) discovered that planning tools like earned value management significantly improve construction project results in Nigeria. Despite these insights, significant gaps remain. Numerous studies concentrate on sectors outside of education, utilize small sample sizes, or employ descriptive methodologies that restrict causal inference. Furthermore, M&E planning is frequently analyzed in a general manner without pinpointing its specific impact within education infrastructure projects, especially in the Kenyan context.

Baseline studies are essential for establishing reference points to measure project progress. Empirical research presents mixed evidence regarding their effect on performance. In Kenya, Wambua and James (2019), Onyango and Pedo (2021), Njeru and Kirui (2022) found that baseline surveys considerably enhance education project outcomes by facilitating improved planning and performance assessment. Likewise, research in Ghana and Rwanda corroborates that thorough baseline evaluations boost adherence to timelines, cost efficiency, and user satisfaction (Kissi et al., 2019). However, other studies indicate weaker or inconsistent effects. For example, Gaibo and Mbugua (2019) reported that baseline studies had a limited impact on the execution of infrastructure projects in Marsabit County. Such inconsistencies may be attributed to differences in how baseline studies are operationalised or implemented. Further gaps include limited sectoral focus, reliance on cross-sectional designs, and insufficient exploration of baseline data quality. Most studies are also conducted outside the education infrastructure context, limiting their applicability to CBC projects in Kenya.

Stakeholder engagement is widely acknowledged as a crucial factor in determining project success. Empirical research conducted in various contexts reveals that participatory M&E improves project outcomes by enhancing transparency, accountability, and stakeholder ownership. In Kenya, research on the Constituency Development Fund (CDF) and infrastructure initiatives indicates that stakeholder involvement is a significant predictor of project performance (Abdi & Kimutai, 2018; Mushori et al., 2020; Leariwala & Kamau, 2021, Wanjohi & Musembi, 2021). Likewise, findings from Spain and Tanzania suggest that participatory M&E promotes social learning, strengthens networks, and improves value-for-money results (Luján Soto et al., 2021; Mnyang’ali & Mathia, 2026). Further studies in Kenya and Uganda corroborate that stakeholder participation enhances the timeliness, cost management, and sustainability of projects (Dakane & Mutuku, 2023; Okullu et al., 2025). However, several limitations are apparent. Numerous studies utilize descriptive or cross-sectional methodologies, which restrict causal interpretations. Others consider stakeholder participation as a broad concept without distinguishing its specific dimensions related to M&E. Additionally, the majority of studies concentrate on sectors such as agriculture, transportation, or community development, with insufficient focus on education infrastructure projects.

Performance reviews serve as an essential feedback tool for enhancing project execution. Research indicates that consistent performance evaluations lead to improved project results by detecting discrepancies and facilitating corrective measures. Seng et al. (2019) discovered that regular evaluations enhance alignment with project goals and overall effectiveness. Likewise, research conducted in Kenya and Ghana demonstrates that performance evaluation processes have a positive effect on timeliness, stakeholder satisfaction, and decision-making (Koima & Mukulu, 2020; Issifu & Agyapong, 2023; Kirori & Karanja, 2019). In the context of infrastructure projects, performance feedback mechanisms have been associated with better outcomes due to increased accountability and adaptive management (Njoroge et al., 2021). Nevertheless, there is evidence suggesting that performance evaluations are not always effectively implemented, especially in environments with limited resources (Nyathi, 2021). Significant gaps exist, including a lack of longitudinal evidence regarding the lasting effects of performance evaluations and inadequate examination of contextual elements such as organizational culture and funding. Furthermore, the majority of existing studies concentrate on sectors outside of education, underscoring the necessity for research focused on CBC infrastructure projects.

3. methodology

This research utilized a descriptive research design. This design is suitable for detailing characteristics, behaviors, and phenomena as they occur in their natural environment (Crowther & Lancaster, 2012). It allows for systematic observation and documentation of M&E practices and project outcomes without altering any variables. The descriptive design is also appropriate when the researcher aims to evaluate relationships between variables (Kothari, 2004). In this research, it enabled the investigation of how M&E practices correlate with the performance of Competency-Based Curriculum (CBC) infrastructure projects in Nairobi City County, Kenya, utilizing indicators such as timeliness, cost efficiency, quality, and achievement of project objectives. The target population included all 101 CBC infrastructure projects executed in Nairobi City County from January 2021 to December 2023. These projects constituted the unit of analysis. The unit of observation comprised 101 public secondary school principals who managed the respective schools where the projects were carried out. These participants were deemed suitable due to their direct engagement in and understanding of M&E processes and project implementation results.

Considering the relatively small and manageable size of the population, a census approach was employed. All 101 CBC infrastructure projects and their associated school principals were incorporated into the study. This method is endorsed by Kothari (2004), who advocates for a census when the population size is small enough to permit complete coverage, thus eliminating sampling error and improving representativeness. Primary data were gathered through semi-structured questionnaires. The questionnaires were distributed to school principals and included both closed-ended and open-ended questions. The structured section utilized a 5-point Likert scale to assess M&E practices and project performance, while open-ended questions allowed respondents to offer additional qualitative insights.

Validity was evaluated in terms of both face and content validity. Content validity ensured that the items in the questionnaire effectively captured the constructs being studied, while face validity examined the clarity and relevance of the items as assessed by experts and respondents (Cohen et al., 2017). Project management specialists reviewed the instruments, and insights from the pilot study were utilized to enhance the tools. Reliability was evaluated through internal consistency measures. The Cronbach’s alpha coefficient was used to assess the consistency among questionnaire items that measure the same constructs, with a threshold of 0.70 deemed acceptable (Marvasti, 2018). Reliability guaranteed the consistency of measurement across repeated uses of the instrument.

Data collection began after receiving authorization from the University Graduate School, followed by research clearance from the National Commission for Science, Technology and Innovation (NACOSTI) and approval from the Nairobi County Director of Education. Schools were visited to inform respondents about the study's purpose and ethical considerations. Questionnaires were distributed using a drop-and-pick-later method, allowing respondents five days to complete them. Follow-up was carried out via telephone and email. Quantitative data were coded and analyzed using the Statistical Package for Social Sciences (SPSS). Descriptive statistics, including frequencies, percentages, means, and standard deviations, were employed to summarize the data. Inferential analysis involved Pearson correlation and multiple regression to ascertain the relationship between M&E practices and project performance. The study employed a multiple linear regression model to examine the effect of M&E practices on the performance of CBC infrastructure projects:

Y=β0+β1X1+β2X2+β3X3+β4X4+ε

Where: Y= Performance of CBC infrastructure projects, X1= M&E planning, X2= M&E baseline studies, X3= Stakeholder participation in M&E, X4= M&E performance reviews, β0= Constant β1-β4= Regression coefficients and ε= Error term.

4. results and discussion

4.1 Introduction

The empirical study distributed 101 questionnaires to principals of various public secondary schools in Nairobi City County, where competency-based curriculum infrastructure projects were implemented. Out of the total distributed, 79 were returned with complete responses, resulting in a response rate of 78.2% (Table 1), which surpasses the 70% threshold, thus ensuring the representativeness of the collected data (Mugenda & Mugenda, 2003). It was determined that the data were sufficient for analysis and reporting. Additionally, an interview was conducted with 8 sub-county directors of education in Nairobi County. This number was determined based on saturation, as further interviews did not provide new insights.

4.2 Descriptive Analysis

Descriptive statistics were employed to analyse the distribution of the study variables. The descriptive statistical analysis utilised percentages, mean and standard deviation. The section has been organised in terms of study variables. The study adopted a 5-point Likert scale on which statements about M&E practices were evaluated. The analysis made use of µ and σ. The study then extracted the overall mean and standard deviation of each construct as presented in Table 1.

Table 1: Overall mean and standard deviation of the study constructs

| Constructs | Overall Mean | Overall Standard deviation |
| --- | --- | --- |
| M&E Planning | 3.80 | 1.09 |
| M&E Baseline Studies | 3.48 | 0.92 |
| Stakeholder Participation in M&E | 3.49 | 0.93 |
| M&E Performance Reviews | 3.76 | 1.12 |
| Project Performance | 3.83 | 1.03 |

The results presented in Table 1 suggested that the participants in the study concurred that some form of M&E planning was executed, as reflected by an aggregate mean of 3.80. The findings on the stakeholder involvement showed a moderate average of 3.48 (SD = 0.92) indicating that the stakeholder participation was below satisfactory and optimal. The analysis of M&E baseline studies in the survey provided the µ of 3.49 and 0.93 sigma, which means that there was a moderate agreement that the activities of the baseline were performed. The survey-based performance reviews indicated a moderate level of agreement between the participants and the average score was 3.76 with a standard deviation of 1.12. The survey revealed that the project outcomes dimension achieved an average score of 3.83 (SD = 1.03), indicating moderate outcomes in cost management, timeliness, and stakeholder satisfaction.

### 4.3 Regression Analysis

Regression analysis builds upon correlation analysis by investigating how independent variables can predict variations in outcome variable. This method makes it possible to examine the impact each predictor has on the outcome variable. In this research, multiple regression analysis was deemed suitable, as it allowed for the concurrent evaluation of the effects of various predictors on project outcomes. The regression model yields coefficients that indicate the sensitivity of project outcome to variation in each aspect of M&E practices, while controlling for other factors.

Table 2: Summary of the Model

| Model | R | R2 | Adj. R2 | S.E | DW |
| --- | --- | --- | --- | --- | --- |
| 1 | .895a | .802 | .788 | .40609 | 2.005 |
| a. Predictors: (Constant X1= ), X1= M&E planning, X2 = M&E Baseline Studies, X3= Stakeholder Participation in M&E, X4= M&E performance reviews |  |  |  |  |  |
| b. Dependent Variable: Project performance c. S.E = Standard Errors, DW= Durbin–Watson statistic |  |  |  |  |  |

In the model summary, (Table 2) the overall correlation coefficient (R = 0.895) depicts a strong link between project outcomes and M&E practices. The Adjusted R Squared = 0.788 showed that 78.8% of the variation in the outcomes of the studied projects was explained by the combined effects of the M&E components. Thus, it was noted that the residual variation of 21.2% of the variance in project outcomes is accounted for by unobserved variables.  In conclusion, the findings presented in the model summary indicated that the collection of M&E variables incorporated in the regression analysis reliably and significantly predicts project performance, rendering the model both statistically robust and theoretically sound.

Table 3: ANOVA

| Model |  | SS | df | MSS | F | Sig. |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Regression | 48.628 | 5 | 9.726 | 58.976 | .000b |
|  | Residual | 12.038 | 73 | .165 |  |  |
|  | Total | 60.667 | 78 |  |  |  |
| a. Dependent Variable: project performance |  |  |  |  |  |  |
| b. Predictors: (Constant), X1= M&E planning, X2 = M&E Baseline Studies, X3= Stakeholder Participation in M&E, X4= M&E performance reviews, c. MSS= mean sum of squares |  |  |  |  |  |  |

Table 3 generated an F-statistic value of 58.976, accompanied by a p-value = 0.00, which signifies that the model holds statistical significance. This indicates that the M&E variables, when considered together, possess considerable predictive power regarding project performance. In other terms, the probability that this relationship arose by chance is exceedingly low. Consequently, the ANOVA results illustrate that the synergistic effect of M&E planning, baseline studies, stakeholder engagement, and performance evaluations plays a significant role in explaining variations in project outcomes. Thus, the overall outcome of the ANOVA confirms that the M&E dimensions, when assessed collectively, are powerful predictors of a successful project.

Table 4: Regression Coefficients

| Model |  | Unstandardized Coefficients |  | Standardized Coefficients | t | Sig. |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | B | Std. Error | Beta |  |  |
| 1 | (Constant) | 3.642 | .156 |  | 23.271 | .000 |
|  | X1 | .341 | .093 | .345 | 3.672 | .000 |
|  | X2 | .265 | .102 | .226 | 2.594 | .011 |
|  | X3 | .363 | .098 | .361 | 3.702 | .000 |
|  | X4 | .058 | .103 | .059 | .562 | .576 |
| - Dependent Variable: Project performance - X1= M&E planning, X2 = M&E Baseline Studies, X3= Stakeholder Participation in M&E , X4= M&E performance reviews, |  |  |  |  |  |  |

The parameter estimates in Table 4 demonstrate how each independent variable individually affects project outcomes while holding the others constant. The intercept term (3.642) signifies the project outcomes level when predictor variables are at a constant level. The individual betas, along with their significance levels, illustrate the relative contribution of each M&E dimension.

Project Performance = 3.645 + 0.345 M&E Planning+ 0.226 M&E Baseline studies+ 0.361Stakeholder participation in M&E + 0.059 M&E performnce reviews+ε

4.4 Discussion of Findings

Planning exhibited a beta of 0.345 with a p- value = 0.00, indicating a strong enhancing effect on project outcomes. The finding depicts that an enhancement in M&E planning resulted in project outcomes improvement. This finding highlights the significance of well-defined planning frameworks, clearly outlined roles, and timely M&E schedules in facilitating project success. The finding is in agreement with Muhayimana and Kamuhanda (2020), who noted that planning strongly enhanced project outcomes. Similarly, Olaremi et al. (2024) indicated that structured M&E planning tools like earned value management and benchmarking significantly improve the outcomes of projects.  M&E Baseline Studies revealed a strong enhancing effect (B2 = 0.226, p = 0.01). This indicates that projects grounded in thorough baseline assessments tend to achieve better performance, as such studies furnish essential data that guide design, resource allocation, and implementation strategies. The finding was in congruence with Onyango and Pedo (2021) in road construction projects in Nairobi, who found that baseline studies had a strong enhancing effect on project outcomes. Additionally, Njeru and Kirui (2022) in construction projects by KeNHA depicted that baseline surveys were central in confirming project scope, thereby aiding in the setting of pragmatic project outcomes, including time, cost, and quality. However, the findings were contrary to Gaibo and Mbugua (2019), who indicated that baseline studies weakly explained the successful implementation.

Stakeholder Participation emerged as another robust predictor of project outcomes (B3 = 0.361, p = 0.00). This signify that the active involvement of stakeholders in the M & E process results in improved project outcomes. When beneficiaries, contractors, and oversight bodies participate actively in M&E activities, accountability and ownership are bolstered, thereby enhancing both the quality and sustainability of project deliverables.  The finding was in agreement with Leariwala and Kamau (2021) in NG-CDF projects, which revealed that participatory M& E predicted project outcomes. Similarly, Wanjohi and Musembi (2021) in road infrastructure projects in Kiambu revealed that stakeholder participation strongly explained project performance. Finally, Moegh (2023) on infrastructure projects in public universities in Nairobi noted that the participation of stakeholders strongly enhanced project outcomes. The M&E Performance Reviews showed a direct effect that was not strong (B4 = 0.058, p = 0.57). The result is evidence that, although performance reviews have a slight contribution to project success, their execution in the sampled projects may not have been adequately consistent or timely to produce a quantifiable impact. It indicates that while review mechanisms are in place, they may not be effectively associated with corrective actions or decision-making processes. The finding was in agreement with Nyathi (2021) in Rural District Councils’ projects in Zimbabwe, which revealed that even though the respondents understood the value of performance reviews, they were rarely done. However, the finding conflicts with Kirori and Karanja (2019), who showed a linear relationship between M&E reporting, dissemination and project outcomes. Similarly, Njoroge et al. (2021) in public sector infrastructure projects found that when project teams receive regular feedback based on performance reviews, they tend to perform better, achieving desired results more efficiently.

5. Conclusion

This research investigated the impact of Monitoring and Evaluation practices on the effectiveness CBC infrastructure projects in Nairobi City County, Kenya. Utilizing descriptive statistics, correlation analysis, and multiple regression modelling, the results indicate that M&E practices are a vital factor influencing project performance, especially concerning cost efficiency, timeliness, quality compliance, and stakeholder satisfaction. The findings reveal that M&E planning serves as a fundamental driver of successful project results. Projects that feature organized planning frameworks, well-defined responsibilities, and systematic implementation schedules consistently demonstrate enhanced performance outcomes. This highlights the necessity of integrating M&E planning during the initial phases of project design to improve coordination, accountability, and decision-making throughout the project lifecycle. Additionally, baseline studies were shown to have a significant positive effect on project performance. Projects that were preceded by thorough needs assessments achieved better alignment between resource allocation and actual infrastructural needs. This affirms that data-driven planning improves the accuracy of budgeting, design, and implementation processes, thus minimizing inefficiencies, delays, and resource misallocation.

Stakeholder participation has emerged as a crucial factor contributing to enhanced project outcomes. The inclusive engagement of school leadership, parents, teachers, and local education stakeholders has improved transparency, ownership, and responsiveness during project implementation. Nevertheless, stakeholder involvement was more evident during the implementation phase than in the initial planning stage, which limited its potential to influence project design and priorities. Conversely, M&E performance reviews, although positively correlated with project outcomes, did not demonstrate a statistically significant predictive effect. This indicates that the current review mechanisms are primarily compliance-focused and inadequately integrated into corrective actions and adaptive management processes. The limited use of feedback from performance reviews diminishes their effectiveness in fostering continuous improvement within CBC infrastructure projects.

The study concludes that M&E practices especially planning, baseline studies, and stakeholder engagement are vital in enhancing the performance of CBC infrastructure projects in Nairobi City County. However, deficiencies in capacity development and the underutilization of performance review findings hinder the overall effectiveness of the M&E system. Therefore, it is essential to strengthen institutional capacity, standardize M&E frameworks, and improve feedback utilization mechanisms to enhance project efficiency, accountability, and sustainability in public school infrastructure development. To enhance project outcomes, it is recommended that schools institutionalise structured M&E planning at the project initiation stage, conduct systematic baseline studies before implementation, and ensure early and inclusive stakeholder engagement in all project phases. Additionally, strengthening capacity-building for school managers and education officers, standardising M&E frameworks, and improving the use of performance review feedback for corrective action are critical for improving efficiency, accountability, and sustainability in CBC infrastructure development.

Competing interests

Authors have declared that no competing interests exist.

References

- Abdi, A. H., & Kimutai, G. (2018). Monitoring and evaluation, and performance of constituency development fund projects in Garissa County, Kenya. International Academic Journal of Information Sciences and Project Management, 3(2), 418 - 445.

- Aloyce, D., Monko, R. J., & Luvara, V. G. (2024). Critical audit indicators for assessing construction projects' performance (CPP) at the pre-contract stage in Tanzania. International Journal of Construction Management, 24(5), 530-539.

- Ayebare, A. (2019). Monitoring and Evaluation Practices and Performance of Road Infrastructure Projects in Uganda: a Case of Uganda National Roads Authority UNRA. Uganda Christian University. Uganda Christian University.

- Cohen, L., Manion, L., & Morrison, K. (2017). Validity and reliability. In Research methods in education (pp. 245-284). Routledge.

- Crowther, D., & Lancaster, G. (2012). Research methods. Routledge.

- Dakane, M., & Mutuku, M. (2023). Stakeholder participation and performance of irrigation projects in Kenya. Strategic Journal of Business & Change	Management, 10(4), 1-15. https://doi.org/10.61426/sjbcm.v10i4.2818

- Elger, D. (2007). Theory of performance. Faculty guidebook: A comprehensive tool for improving faculty performance (Vol. 1).

- Elle, S. M. (2022). The role of corporate governance in the management of physical public infrastructures in some selected Sub-Saharan African countries. 6(1), . Journal of Infrastructure, Policy and Development, 6(1), 1382- 1397.

- Freeman, R. E. (1984). Strategic management: A stakeholder approach. Boston:Pitman.

- Gaibo, G. S., & Mbugua, J. (2019). Influence of monitoring and evaluation practices on the implementation of county governments’ infrastructural development projects in Marsabit County, Kenya. International Academic Journal of Information Sciences and Project Management, 3(5), 184-217.

- Issifu, I., & Agyapong, A. (2023). The influence of monitoring and evaluation practices on technology start-up performance in Ghana. Journal of Innovation and Entrepreneurship, 12(3), 45–61. https://doi.org/10.1186/s13731-023-00245-7

- Kamau, J., & Muchelule, Y. (2024). The effect of participatory monitoring and evaluation on livelihood development project performance in Somaliland. International Journal of Social Sciences Management and Evaluation, 6(1), 23-41.

- Kihuha, P. (2018). Monitoring and Evaluation Practices and Performance of Global Environment Facility Projects in Kenya, a Case of United Nations Environment Programme. Master's Thesis, Kenyatta University.

- Kirori, G. M., & Karanja, D. N. (2021). Monitoring and evaluation practices and performance of youth projects in non-governmental organisations in Kenya. Nairobi.

- Kissi, E., Agyekum, K., Baiden, B. K., Tannor, R. A., Asamoah, G. E., & Andam, E. T. (2019). Impact of project monitoring and evaluation practices on construction project success criteria in Ghana. Built Environment Project and Asset Management, 9(3), 364 -374.

- Koima, D., & Mukulu, E. (2020). Effect of monitoring and evaluation systems on agricultural research project performance under KALRO, Kenya. Journal of	Agricultural Extension and Research, 28(4), 55–70. https://doi.org/10.4314/jaer.v28i4.4

- Kothari, C. R. (2004). Research methodology: Methods and techniques. New Delhi: New Age International.

- Leariwala, J. L., & Kamau, L. N. (2021). Participatory monitoring and evaluation practices and performance of selected national government constituency development fund projects in Samburu County, Kenya. Unpublished Master's Thesis, Kenyatta University.

- Luján Soto, R., Cuéllar-Padilla, M., Rivera Méndez, M., Pinto-Correia, T., Boix-Fayos, C., & de Vente, J. (2021). Participatory monitoring and evaluation to enable social learning, adoption, and out-scaling of regenerative agriculture. Ecology and Society, 26(4), 29.

- Mnyang’ali, E., & Mathia, J. (2026). Stakeholder participation in monitoring and evaluation systems and value for money in local government projects in	Tanzania. African Journal of Empirical Research, 7(1), 1-15 https://doi.org/10.51867/ajernet.7.1.100

- Marvasti, A. (2018). Research methods. The Cambridge handbook of social problems,1(3), 23-37.

- Mayne, J. (2007). Challenges and Lessons in Implementing Results-Based Management. Evaluation, 13(1), 87-109.

- Moegh, F. K. (2023). Stakeholder involvement and performance of construction projects in public universities in Nairobi City County, Kenya. Master's Thesis, Kenyatta University, Nairobi.

- Mugenda, O. M., & Mugenda, A. G. (2003). Research methods: Quantitative & qualitative approaches. Nairobi: Acts Press.

- Muhayimana, O., & Kamuhanda, J. K. (2020). The relationship between Monitoring and Evaluation practices and public projects performance in Rwanda with reference to Science and Technology Skills. International Journal of Advanced Scientific Research, 5(9), 98 - 110.

- Mushori, J., Machira, F. A., & Matu, J. (2020). Determinants of Effective Monitoring and Evaluation: Pre-requisite for County Government Funded Infrastructural Development Projects. International Journal of Innovative Research & Development, 9(4), 311-325.

- Njeru, C. M., & Kirui, C. (2022). Monitoring and Evaluation Practices and Performance of Kenya National Highway Authority Road Construction Projects in Nairobi City County, Kenya. Journal of Entrepreneurship & Project Management, 2(1), 11-27.

- Njoroge, M. O., Nyang'au, S. P., & Nyamwaro, L. K. (2021). Monitoring, Evaluation and Performance of Kenya National Highways Authority Projects in Nairobi, Kenya. International Journal of Social Sciences Management and Entrepreneurship, 6(5), 22-34.

- Nyathi, L. (2021). Influence of monitoring and evaluation practices on rural district councils’ project performance. A case of the Bubi district council project in Zimbabwe. Harare: Unpublished Master's Thesis, Africa Nazarene University.

- Office of the Auditor General. ([OAG], 2024). Auditor Generals Report on National Government 2022/2023. Office of the Auditor General.

- Okullu, P., Karimi, P., & Wamalwa, F. (2025). Stakeholder engagement in monitoring and evaluation and performance of the Parish Development Model in Uganda.	International Journal of Sustainable Development and Construction.2(8),1-15https://ijsdc.org/storage/xq6TzRAqpbBh89kGqBR6Odqmkoo5ilfWpezYWd	n.pdf

- Olaremi, S. O., Dada, A. D., Lawal, A. F., Adisa, E., Ojefia, E. F., & Garbati, A. A. (2024). Monitoring and Evaluation Practices on Building Construction Project Delivery among Tertiary Institutions of Ondo State, Nigeria. Journal of Applied Sciences and Environmental Management, 28(12), 4007-4017.

- Onyango, W. A., & Pedo, M. (2021). Monitoring and Evaluation Practices and Performance of Road Projects in Nairobi City County, Kenya. International Journal of Social Sciences Management and Entrepreneurship, 6(7), 3-21.

- Pereira, L., Dias, Á., Costa, R. L., & Gonçalves, R. (2022). (2022). How to improve performance in public investment projects. International Journal of Procurement Management, 15(2), 219-235.

- Seng, T., Chan, S., & Kumar, R. (2019). The role of performance reviews in enhancing project management success. Journal of Project Management, 15(2), 45-58.

- Tarindwa, H. H. (2019). Influence of monitoring and evaluation practices on the performance of government sponsord arts projects in Namibia: A case of national arts council on Namibia. Africa Nazarene University. Africa Nazarene University.

- UNDP. (2011). Handbook on Planning, Monitoring and Evaluating for Development Results. United Nations Development Programme.

- Wambua, C. M., & James, R. (2019). Monitoring And Evaluation Practices And Performance Of County Funded Education Projects In Makueni County, Kenya. Kenyatta University.

- Wanjohi, N. M., & Musembi, A. (2021). Project Monitoring and Evaluation Practices and Performance of Road Infrastructural Projects in Kiambu County, Kenya. International Journal of Social Sciences Management and Entrepreneurship, 8(3), 3-17.